## Slide 1
Release and Iteration Planning
A Module in Agile Fundamentals
This work is licensed under the
Creative Commons Attribution-ShareAlike 4.0 International License.
To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/4.0/.
Notes: Plan, execute and report on Agile projects
--------------------------------------------------------------------------------------------------------------------
In this module, we’ll explore the practices that help Managers and Project Managers plan, execute, and report on Agile projects.
1
Release and Iteration Planning

## Slide 2
Questions To Be Answered
What are you going to build?
In what order?
How long is it going to take?
How much will it cost?
What roles and how many do we need?
What else do we need to do?
Notes: Answered the basic “how long” in Estimating section.
2
Release and Iteration Planning

## Slide 3
Release Success Criteria
Quantifiable business objectives
ROI
Time
Budget
Scope
Notes: What is driving the Release?
Time, budget, scope
Market pressure for functionality
Launch of a new project
Are there quantifiable objectives / ROI that need to be met?
3
Release and Iteration Planning

## Slide 4
Release Planning
Development Capacity (Velocity)
Release Success Criteria
Initial Story List
Release Constraints
Dependencies
High level tech architecture
Cross Functional Requirements
The Release Planning Inputs
Notes: We need to understand the:
Release success criteria. Time driven, scope driven, $ driven.
Development capacity
Constraints - resource, technical, skill level
Project dependencies
A high level application architecture
Non functional or cross functional requirements – all the ‘abilities
----------------------------------------------------------------------------------------------------------
Like most things in an Agile world, release planning is an iterative and adaptable process. Depending on how the first cut at a release plan may look, more effort may be put into loosening the hold of external constraints (e.g., marketing schedules) or the success criteria for the release may be re-examined (e.g., perhaps another pass through MoSCoW on the story list).
Development Capacity can either be estimated (using a sampling of different story sizes and extrapolating) or determined using a spike iteration.
The success criteria for the project are probably enumerated across the lines of scope (e.g., “we must have these features at least”), cost (e.g., “we only have budget for $200 of development”) and time (“we need to get something to market before the conference starts”).
External constraints can have a big influence on the release plan and are often in the shape of project dependencies (i.e., integrating with Application X which only releases each quarter).
A release story wall can be used to show the distribution of stories between releases and between iterations within a release. Obviously a release plan is a high level artifact, so the expectation should be set to allow considerable movement at this level.
Low: 2 min
High: 5 min
4
Release and Iteration Planning

## Slide 5
MoSCoW Prioritization
Must Have
Should Have
Could Have
Won’t Have
POINTS
Notes: Most likely the total bucket of stories will can be categorized into these four buckets. For the purposes of planning the first release, the MMR should be the Must Have bucket.
5
Release and Iteration Planning

## Slide 6
Span Planning
Goal
Activity
Story
Goal
Goal
Activity
Activity
Activity
Story
Story
Story
Story
Story
Story
Story
Story
Story
Story
Story
Story
Story
Time
Necessity
MMF
Notes: There are many versions of this approach, but in essence its about laying out the stories so that you can see where the MMF is.
The next slide shows an example from Jeff Patton
When prioritizing stories and building the Release Plan, consider the following:
Business Value – does this contribute to the ROI. What is the Minimum Marketable Feature set?
Risk – does the item carry either technical or functional risk
Usage – How often is this feature set used and by how many different roles/personas?
Compliance – is the feature set required to avoid possible financial penalties?
Dependencies - is this feature set dependent on or required by another team?
Simplicity – do we need all parts/stories for this feature set? Or can we go Live with a subset?
6
Release and Iteration Planning

## Slide 7
Dependencies
Cross project dependencies
Departmental dependencies
Staffing dependencies

## Slide 8
Cross-Functional Requirements
Portability
Extensibility
Localization
Scalability
Usability
Auditability
Authentication
Authorization
Availability
Performance
Regulatory
Security
Execution
Evolution
Notes: Another type of requirement that has to be captured on all projects is the NFR.
We all know what these are. They creep up on us near the end.
Execution qualities of a system – security, usability
Evolution qualities – testability, extensibility, scalability
NFRs are typically technical or usage based and usually follow policy or documented guidelines
Make them cards.
Its work you have to do.
HAVE SOME DISCUSSION HERE as to what you can do about these.
Technique-
Send out a questionnaire first for folks to do their homework.
How many transactions/users/countries/whatever?
Response time?
What platforms?
Compliance
Low: 5min
High: 15min
8
Release and Iteration Planning

## Slide 9
In Summary
Prioritizing stories
Minimally Marketable Features
Span Planning
Other activities
Notes: 9
Release and Iteration Planning

## Slide 10
What goes into each release?
MMF = 1,297pts
Priority 2 – 873 pts
The rest – 520 pts

## Slide 11
Questions?
Notes: 11
Release and Iteration Planning